## Sheet1
Day | Ideal Remaining Points | Actual Remaining Points
0 | 40 | 40
1 | 36 | 38
2 | 32 | 35
3 | 28 | 30
4 | 24 | 28
5 | 20 | 22
6 | 16 | 18
7 | 12 | 12
8 | 8 | 8
9 | 4 | 5
10 | 0 | 0

## Sheet2
User Story ID | Description | Story Points | Responsible Role
1 | Set up Raspberry Pi | 5 | Developer
2 | Collect data | 8 | Developer
3 | Clean and scale data | 5 | Developer
4 | Make data plots | 3 | Developer
5 | Build regression model | 8 | Developer
6 | Evaluate model | 5 | Developer
7 | Use GitHub | 3 | Developer
8 | Create video demo | 3 | Developer